Gujarat Pipavav Port Limited

Tender Document

Design, Procure and Construction of Immigration Office at APM Terminals Pipavav

GPPL-BID-001

Volume – 1

Section 3	: Conditions of Contract

##### GUJARAT PIPAVAV PORT LIMITED

DESIGN PROCURE AND CONSTRUCTION IMMIGRATION OFFICE AT APM TERMINALS PIPAVAV

##### CONDITIONS OF CONTRACT

##### PART I – GENERAL CONDITIONS OF CONTRACT

The Conditions of Contract, Part I – General Conditions of Contract shall be those forming Part I of the “Conditions of Contract for Plant and Design Build” first edition 1999, with further amendments, prepared by the Fédération Internationale des Ingénieurs-Conseils (FIDIC). These Conditions are subject to the variations and additions set out in Part II hereof entitled “Particular Conditions of Contract.”

The FIDIC “Conditions of Contract for Plant and Design - Build”, mentioned above are not included with the present Bid Documents. Copies of the FIDIC “Conditions of Contract for Plant and Design - Build” can be obtained from the:

FIDIC Secretariat and Bookshop Geneva Airport

Box 311, 29 Route de Pré-Bois, Cointrin CH-1215 Geneva 15

Switzerland

Tel		: + 41 22 799 49 00	Fax	:+ 41 22 799 49 01

Website	:  www.fidic.org		E mail	: fidic.pub@fidic.org

##### PART II – PARTICULAR CONDITIONS OF CONTRACT

The Part II – Particular Conditions of Contract (PCC) constitute amendments and additions to the Part I – General Conditions of Contract (GCC). Clause numbers in this part correspond to those in the Part I – GCC, except for clauses with numbers higher than 20.8. Clauses, having numbers higher than 20.8, are to be construed as additional clauses to the Part I – GCC.

In the event of a conflict or inconsistency between the Part I (GCC) and the Part II (PCC), the provisions stipulated in the Part II (PCC) shall prevail over and supersede those of Part I (GCC).

| Clause – 1 : General Provisions |  |
| --- | --- |
| Sub clause 1.1.3.7 Defects Notification Period | Delete the Sub-Clause 1.1.3.7 and substitute: "Defects Notification Period" means the period for notifying defects in the Works or a Section (as the case may be) under Sub-Clause 11.1 [Completion of Outstanding Work and Remedying Defects], as stated in the Appendix to Tender (with any extension under Sub-Clause 11.3 [Extension of Defects Notification Period]), calculated from the date on which the Works or Section is completed as certified under Sub-Clause 10.1 [Taking Over of the Works and Sections]. and which shall extend for a period of 24 months unless otherwise specified. |
| ##### Sub-Clause 1.1.6.8 ##### Unforeseeable | Delete the Sub-Clause 1.1.6.8 and substitute: "Unforeseeable" means not reasonably foreseeable by the Date for the Return of Priced Tenders. |
| ##### Sub-Clause 1.1.6.9 ##### Management Meeting | Add the following at end of sub clause 1.1.6.9: "Management Meeting" means a meeting called by either the Engineer or the Contractor's Representative in accordance with Sub-Clause 3.6. |
| ##### Sub-Clause 1.1.6.10 Third Party Code of Conduct | Add the following new Sub-Clause 1.1.6.10 after Sub-Clause 1.1.6.9 “Third Party Code of Conduct” means the APM Terminals Third Party Code of Conduct as included in Appendix A100_5. |
| ##### Sub-Clause 1.1.6.11 Employer’s Auditor | Add the following new Sub-Clause 1.1.6.11 after Sub-Clause 1.1.6.10 “Employer’s Auditor” means an internationally reputed third-party auditor, appointed by the Employer at his own cost, charge and expense. |
| ##### Sub-Clause 1.2 Interpretation | Add the following after (d) in the Sub-Clause: - The word "Tender" is synonymous with "Bid". Add the following at the end of the Sub-Clause: In these Conditions, provisions including the expression "Cost plus reasonable profit" require this profit to be (5%) of this Cost. |
| ##### Sub-Clause 1.8 ##### Care and Supply of Document | Delete the last paragraph of the Sub-Clause and substitute: If a Party becomes aware of an error or defect in a document which was prepared for use in executing the Works, the Party shall promptly give notice to the other Party of such error or defect. |

| ##### Sub-Clause 1.9 ##### Errors in the Employer Requirements | Add the following at the end of the Sub-Clause: I If the error occurred is due to design fault of the Contractor, then Client shall not pay any amount on error construction & will be solely responsibility of the Contractor. |
| --- | --- |
| ##### Sub-Clause 1.12 Confidential Details | Add the following new paragraph at the end of the Sub-Clause: The Contractor shall treat the details of the Contract and the Employer’s operations and affairs as private and confidential, save in so far as may be necessary for the purposes the Contract, and shall not publish or disclose the same or any particulars thereof in any trade or technical paper or elsewhere without the previous consent in writing of the Employer or the Engineer. If any dispute arises as to the necessity of any publication or disclosure for the purpose of the Contract the same shall be referred to the decision of the Employer whose award shall be final. The Confidentiality provision shall extend to the Contractor and Contractor’s Personnel. |
| ##### Sub-Clause 1.13 ##### Compliance with Laws | Sub-paragraph (b) is amended to The Contractor shall give all notices, pay all taxes, duties and fees, and obtain all permits, building permits, licences and approvals, as required by the Laws in relation to the execution and completion of the Works including for the design of any part of the Works for which he is responsible and the remedying of any defects; and the Contractor shall indemnify and hold the Employer harmless against and from the consequences of any failure to do so. INSERT at the end of Sub-Clause 1.13: (c) and The business contact information regarding a Party’s personnel and/or third parties engaged by it may be shared for the purposes of maintaining the contractual business relationships between the Parties, e.g. contract management of the contract, payments and/or business development. The Parties shall handle such business contact information according to their privacy policies and practices. It is each Party’s responsibility to have a legal basis (i.e. privacy notice, consent, etc.) for sharing such business contact information with the other party. Maersk’s global privacy policy is available at www.maersk.com. The Parties may transfer such information to any country where their global organization operates and hereby authorizes such transfer per se and on behalf of such personnel and/or third parties. If required by applicable laws, the Parties agree to sign any additional document required to allow the transfer of such data outside its country of origin. In the event of any difference between the Contract and the any applicable law, the requirement for the stricter obligation or standard shall prevail. |
| ##### New Sub-Clause 1.15 corrupt, fraudulent practice | Add the new sub clause 1.15 after sub clause 1.14: “If the Employer determines that the Contractor and/or any of its personnel, or its agents, or its Subcontractors, sub-consultants, services providers, suppliers and/or their employees has engaged in corrupt, fraudulent, collusive coercive, or obstructive practices, in competing for or in executing the Contract, then the Employer may, after giving 14 days’ notice to the Contractor, terminate the Contractor's employment under the Contract and expel him from the Site, and the provisions of Clause 15 shall apply as if such expulsion had been made under Sub-Clause 15.2. For the purposes of this Sub-Clause, - “corrupt practice” means the offering, receiving, or soliciting, directly or indirectly, of anything of any value to influence the actions of a public official in the selection process or in contract execution; - “fraudulent practice” means a misrepresentation or omission of facts in order to influence a selection Process or the execution of a contract; - “collusive practice” means a scheme or arrangement between two or more Tenderers, with or without the knowledge of the Employer, designed to establish prices at artificial, non-competitive levels; - “coercive practice” means harming or threatening to harm, directly or indirectly, person or their property to influence their participation in a procurement process, or affect the execution of a contract. - “obstructive practice” is - deliberately destroying, falsifying, altering or concealing of evidence material to the investigation or making false statements to investigators in order to materially impede an Employer’s investigation into allegations of a corrupt, fraudulent, coercive or collusive practice; and/or threatening, harassing or intimidating any party to prevent it from disclosing its knowledge of matters relevant to the investigation or from pursuing the investigation, or acts intended to materially impede the exercise of the Employer’s inspection and audit rights. |

| Clause – 2 : The Employer |  |
| --- | --- |
| ##### Sub-Clause 2.1 ##### Right of Access to the Site | Delete the second paragraph of the Sub-Clause and substitute: If no such time is stated in the Appendix to Tender, the Employer shall give the Contractor right of access to, and possession of, the Site within such times as may be required to enable the Contractor to proceed without disruption in accordance with the programme submitted under Sub-Clause 8.3 (Programme). |
| Sub-Clause 2.4 Employer’s Financial Arrangements | Delete the last sentence of the Sub-Clause and substitute: Before the Employer makes any material change to his financial arrangements, the Employer shall give notice to the Contractor with detailed particulars. |
| Clause – 3 : The Engineer |  |
| ##### Sub-Clause 3.1 Engineer's Duties and Authority | Delete the third paragraph of the Sub-Clause and substitute: The Engineer may exercise the authority attributable to the Engineer as specified in or necessarily to be implied from the Contract. The Engineer shall not take any final decision under any of the following Clauses of the Contract unless he has obtained the Employer’s specific written approval (after having given his initial determination to the Employer): - Sub-Clause 8.4 [Extension of Time for Completion] - award any extension to the Time for Completion; - Sub-Clause 8.8 [Suspension of Work] - order any suspension of the whole of the Works; - Sub-Clause 10.1 [Taking Over of the Works and Sections] - issue the Taking Over Certificate; - Sub-Clause 12.3 [Evaluation] - Sub-Clause 13.3 [Variation Procedure] - order any Variation or approve any quotation therefor from the Contractor (other than in the case of a Variation which is urgently required for the safety of the Works or personnel or property on or adjacent to the Site); or Sub-Clause 20.1 [Contractor’s Claims] - approve any adjustment to the Contract. |
| ##### Sub-Clause 3.4 Replacement of the Engineer | Delete the last sentence of the Sub-Clause and substitute: If the Contractor considers the intended replacement to be unsuitable, he has the right to raise reasonable objection against him by notice to the Employer, with supporting particulars, and the Employer shall give full and fair consideration. |

| ##### Sub-Clause 3.5 ##### Determinations | ##### Add new paragraph to the end of the Sub-Clause: ##### If dispute resolution proceedings are not commenced under Clause 20 [Claims, Disputes and Arbitration] within 28 days of the Engineer giving the Parties notice of a determination, such determination shall become final and binding on the Parties and may not be challenged under Clause 20 [Claims, Disputes and Arbitration]. |  |
| --- | --- | --- |
| ##### New Sub-Clause 3.6 Meetings | Add the following new Sub-Clause 3.6 after Sub-Clause 3.5: “The Engineer and the Contractor’s Representatives (Sub-Clause 1.1.2.5 and 4.3) shall attend progress review meetings called by the Employer to review the progress of the Works and other issues related with the Contract. The Engineer shall record the business of such meetings and supply copies of the record to the Employer, Contractor and other concerned persons/authorities. In the record of meetings, the responsibility for any actions to be taken shall be in accordance with the Contract.”. |
| Clause – 4 : The Contractor |  |
| ##### Sub-Clause 4.1 Contractor’s General Obligations | At the end of Sub-Clause 4.1 INSERT: Any documents other than Contractor’s Documents which are required to be submitted to the Engineer for approval under this Contract shall be submitted to the Engineer and the Engineer shall respond to the submittal within 14 days of receipt. If the document is returned to the Contractor marked as either “rejected” or “subject to comments”, then the Contractor shall resubmit the same to the Engineer within 7 days from receipt of the document, addressing the comments raised. The Engineer shall then respond within a further 7 days. For the avoidance of doubt, Contractor’s Documents shall be submitted for approval in accordance with Sub-Clause 5.2 [Contractor’s Documents]. |

| ##### Sub-Clause 4.2 Performance Security | Delete the second paragraph of the Sub-Clause and substitute: The Contractor shall deliver the Performance Security to the Employer within 14 days after receiving the Letter of Acceptance and shall send a copy to the Engineer. The Performance Security shall be issued by a well-known national/scheduled bank to be approved in advance in writing by the Employer and shall be in the form annexed as Section 5 or in another form approved by the Employer. Delete the fourth paragraph of the Sub-Clause and substitute: The Employer shall not make a claim under the Performance Security, except for amounts to which the Employer is entitled under the Contract. Add the following paragraph at the end of to this Sub-Clause: Without limitation to the provisions of the rest of this Sub-Clause, whenever the Engineer determines an addition or a reduction to the Contract Price as a result of a change in cost and/or legislation or as a result of a Variation amounting to more than 25 per cent of the portion of the Contract Price payable in a specific currency, the Contractor shall at the Engineer's request promptly increase, or decrease, as the case may be, the value of the Performance Security in that currency by an equal percentage. |
| --- | --- |
| ##### Sub-Clause 4.3 Contractor’s Representative | INSERT at the end of Sub-Clause 4.3: The Contractor's Representative and all these persons shall also be fluent in English. |
| ##### Sub-Clause 4.4 ##### Sub-Contractors | Delete Sub-Clause 4.4 and substitute the following The Contractor shall not subcontract: (a) the whole or substantially the whole of the Works; (b) the Contractor’s project management functions and obligations under the Contract; (c) the Contractor’s obligations for quality control; (d) the Contractor’s obligations for safety; or (e) the Contractor’s obligations for environmental management. The Contractor shall be responsible for the acts or defaults of any Subcontractor (including a nominated subcontractor), his agents or employees, as if they were the acts or defaults of the Contractor. |
|  | Unless otherwise stated in the Contract the Contractor shall not be required to obtain consent to: (f) suppliers of Materials where the value of such supply does not exceed the equivalent of INR 30,00,000, (g) a subcontract where the value of such subcontract does not exceed the equivalent of INR 30,00,000; or The prior consent of the Engineer (including of the terms of the proposed subcontract) shall be obtained to other proposed suppliers of Materials and Subcontractors; The Contractor shall, when seeking consent to subcontract part of the Works in accordance with this Sub-Clause provide the Engineer with the following: (h) details of the value of the subcontract; (i) evidence to confirm that the proposed Subcontractor is experienced and competent in the relevant work proposed to be subcontracted and is properly registered or licensed to undertake the work; and (j) any such other information as the Engineer may reasonably require. The Contractor shall give the Engineer not less than 28 days’ notice of the intended date of the commencement of each Subcontractor’s work, and of the commencement of such work on the Site; Each subcontract shall include provisions which would entitle the Employer to require the subcontract to be assigned to the Employer under Sub-Clause 4.5 [Assignment of Benefit of Subcontract] (if or when applicable) or in the event of termination under Sub-Clause 15.2 [Termination by Employer]. The Contractor shall ensure that the requirements imposed on the Contractor by Sub-Clauses 1.12 [Confidential Details], Sub-Clause 4.8 [Safety Procedures] (excepting sub-paragraph (d)), paragraph 1 of Sub-Clause 4.9 [Quality Assurance], Sub-Clauses 4.14 [Avoidance of Interference], Sub-Clause 4.18 [Protection of the Environment], and Clause 6 [Staff and Labour] apply equally to each Subcontractor. Where practicable, the Contractor shall give a fair and reasonable opportunity for contractors from India to be appointed as Subcontractors. |
| Sub-Clause 4.6 Cooperation | Delete Sub-Clause 4.6 and substitute the following The Contractor shall, as specified in the Contract or as instructed by the Engineer, allow appropriate opportunities for carrying out work to: - the Employer and the Employer’s Personnel, - any other contractors employed by the Employer - any contractors engaged on the Site by any third party with the approval of the Employer or the Engineer, and - the personnel of any legally constituted public authorities of the Country, who may be employed in the execution on or near the Site of any work whether or not included in the Contract. The Contractor shall be responsible for his construction activities on the Site and shall coordinate his own activities with those of the third-party contractors to the extent (if any) specified or inferred from the Specifications or as shall otherwise become known (or ought to become known) to the Contractor. The Contractor shall not hinder or obstruct the third-party contractors’ activities on Site. If the Contractor cannot resolve issues arising with the coordination of the third-party contractors, the Contractor shall request a decision from the Engineer. The Engineer’s decision on all co-ordination matters shall be final and binding unless or until opened up, reviewed and revised pursuant to Sub-Clause 20.6 [Arbitration]. The Contractor agrees to allow the Employer, the Employer’s Personnel, their respective agents and advisers and any other persons authorised in writing by the Employer or the Engineer such access to the Site and to documentation in relation to the Contract at such times as the Employer shall reasonably require. The Contractor shall assist and co-operate with the Employer, the Employer's Personnel and any contractors engaged by the Employer for the supply of the operating equipment to be used on the completed works in installation and commissioning the operating equipment and its effective integration with the Works so as to enable the successful completion of all inspections and Tests on Completion. Without limiting the foregoing, the Contractor shall make available: - that portion of the Works required for installation and commissioning of the operating equipment by the applicable time for completion and allow the relevant Employer's contractors access thereto; and - to the relevant Employer's contractor, the power supply and other utilities required for installation and commissioning of the operating equipment. The Contractor shall obtain, co-ordinate and submit to the Engineer for his information all details of the proposed works (insofar as they may affect the execution and construction of the Works) of any of the above parties. The Contractor shall be responsible for the locations of their work or materials, in order to ensure that there is no conflict with the work of the Contractor or his subcontractors. The Employer shall give the Contractor all necessary authorisations within the Employer’s possession to enable the Contractor to comply with this Sub-Clause. The Contractor shall indemnify and hold harmless the Employer, the Employer's Personnel, and their respective agents, against and from all claims, damages, losses and expenses in respect of any claim made or proceedings brought by any authorised access to the Site and to documentation in relation to the Contract in accordance with this Sub-Clause 4.6 [Co-operation] arising as a result of the Contractor's or his Subcontractors' presence or negligence or wilful misconduct upon such property or failure to comply with the obligations set out in this Sub-Clause 4.6 [Co-operation]. |
| ##### Sub-Clause 4.7 Setting Out | Add the following paragraph at the end of the Sub-Clause: The Contractor shall give to the Engineer not less than 48 (Forty-Eight) hours’ notice of his intention to set out or give levels for any part of the Works so that timely arrangement may be made for checking or issuing instructions. He shall indicate therein by which date the information, if any is required by him. |
| ##### Sub-Clause 4.8 Safety Procedure | Delete sub-paragraph (a) and replace as follows; - comply with all applicable safety regulations as well as the detailed health and safety requirements as defined in the Specification including the development of an approved Safety Management Plan and instructions form the Engineer and the Employer; In sub-paragraph (c) after “obstruction” and before “so” INSERT “and keep Contractor’s Equipment in a state” Delete “and” from the end of sub-paragraph (d) and Replace “.” with “, and” at the end of sub-paragraph (e). Add a new sub-paragraph (f) at the end of sub-Clause 4.8: “(f) The Contractor shall also take adequate precautions to ensure that his operations do not present any hazard to the navigation and other operations in the sea around the Site.” |
| Sub-Clause 4.9 ##### Quality Assurance | Delete the second paragraph of the Sub-Clause and substitute: The Contractor shall be responsible for quality management of the Works including the implementation of his quality management system and the development, submission and implementation of an approved Project Quality Plan in accordance with the requirements of the Specification. |
| Sub-Clause 4.10 Site Data | Add the following paragraph at the end of the Sub-Clause: Data made available by the Employer, in accordance with this Sub-Clause, shall be deemed to include data listed elsewhere in the Contract as open for inspection at the Employers offices. |
| ##### Sub-Clause 4.12 Unforeseeable Physical Conditions | Delete the words “to the Engineer” in line 2 of the second paragraph and replace by “to the Employer and to the Engineer”. |
| ##### Sub-Clause 4.13 ##### Rights of Way and Facilities | Add the following paragraph at the end of the Sub-Clause: The Contractor shall apply to the Employer for the use of an area of land sufficient for the Contractor's work area, in close proximity to the Site. This work area shall be sufficient to accommodate the Contractor's site offices and all material storage, fabrication and testing facilities which the Contractor desires or which are required under the Contract. |
| ##### Sub-Clause 4.14 Avoidance of Interference | Add the following after the sub-clause (b): (c) the terminal operations of the Employer or of the other operators on the Site. (d) the activities of other parties carrying out works in the vicinity of the Site or within areas for which the Contractor has been granted Non-exclusive Right of Access in accordance with the requirements of the Specification. The Contractor accepts the priority of the Employer’s port / terminal operations with regard to his own activities. |
| ##### Sub-Clause 4.15 ##### Access Route | Add the following paragraph after the sub-clause (e): (f) The Contractor shall comply with all the access requirements of Site security / access / egress arrangements and in particular the requirements of the Employer. Add the following paragraphs at the end of the Sub-Clause: In case any operation connected with the traffic / access necessitates diversion, obstruction or closure of any road, railway or any other "right of way" the approval of the Engineer, the Employer and the respective competent authorities shall be obtained well in advance by the Contractor at their own costs. Access routes shall also include access by sea. The Contractor shall at all times observe and comply with all Laws, including regulations and orders relating to navigation and anchoring of floating plant to be used throughout the Works and any instruction that may be given by the Engineer. The Contractor shall carry out his work strictly in an approved manner and as agreed from time to time with the Employer and Engineer. |
| ##### Sub-Clause 4.18 Protection of the Environment | Delete the last paragraph and substitute: The Contractor shall ensure that emissions, surface discharges and effluent from the Contractor's activities shall not exceed the values stated in the Specification or prescribed by applicable Laws. |
| ##### Sub-Clause 4.19 Electricity, Water and Gas | Delete the first paragraph and substitute: The Contractor shall be responsible for ascertaining, securing and providing all power, water, wastewater, gas, telecommunications and other services to and within the Site as necessary for the completion of the Works. The Contractors arrangements in this regard shall comply with the requirements of the Contract including the detailed requirements defined in the Specification. |
| ##### Sub-Clause 4.20 Employer’s Equipment and Free- Issue Material | Add the following paragraph at the end of the Sub-Clause: The Employer’s port operational equipment shall not be available to the Contractor unless authorization in writing is provided by the Employer and the Engineer. |
| ##### Sub-Clause 4.22 Security at Site | Add the following paragraph and end: The Contractor shall ensure the security of the Site during the whole period of execution and shall be responsible for taking the necessary steps to prevent any loss or accident, which may result from carrying out the Works. The Contractor shall take all essential steps, on his own responsibility and at his expense, to ensure that existing structures and installations on the Site are protected, preserved and maintained. |
| ##### Sub-Clause 4.23 ##### Contractors Operations on Site | Delete second paragraph and substitute; During the execution of the Works, the Contractor shall keep the Site free from all unnecessary obstruction and shall store or dispose of any Contractor’s Equipment or surplus materials. The Contractor shall clear away and remove from the Site any wreckage, rubbish and Temporary Works which are no longer required. The Contractor shall be responsible for site maintenance, cleaning and waste management in accordance with the detailed requirements of the Specification. |
|  | Prior to the submittal of the Contractor’s application for a Taking-over Certificate for a Section, the Contractor shall undertake final cleaning of all completed permanent Works to remove all surplus material, construction debris, wreckage and rubbish. Drainage elements shall be flushed clean to remove any accumulated material and all other service pits shall be cleaned out with particular attention to any pit drainage or weepholes. The frames of all cast iron service pit access covers shall be cleaned and greased. The final cleaning of the site shall be to the satisfaction of the Engineer. |
| ##### New Sub-Clause 4.25 Third Party Code of Conduct | Add the following new Sub-Clause 4.25 after Sub-Clause 4.24 The Contractor shall, in performing the Contract, adhere to the Third-Party Code of Conduct. In the event of any difference between the Contract and the Third-Party Code of Conduct, the document providing for the stricter obligation or standard shall prevail. |
| ##### New Sub-Clause 4.26 Breach of Third-Party Code of Conduct | Add the following new Sub-Clause 4.26 after Sub-Clause 4.25 If the Contractor breaches the Third Party Code of Conduct or fails to collaborate with the Employer’s Auditor during an audit under Sub-Clause 4.28 [Compliance Auditing], and any such breach or failure has not been remedied to the satisfaction of the Employer within 28 days of receipt by the Contractor of a notice from the Employer requiring the Contractor to remedy the same (or such longer period as may be specified in the said notice), the Employer shall be entitled to terminate the Contract in accordance with Sub-Clause 15.2 [Termination by Employer]. |
| ##### Sub-Clause 4.27 Anti-Corruption and Export Control Compliance | Add the following new Sub-Clause 4.27 after Sub-Clause 4.26 The Contractor shall, in performing the Contract, undertake and represent that it and all of its affiliates, directors, officers or sub-contractors will comply in all material respects with all applicable laws, rules, regulations or similar instruments including relating to anti-corruption, competition law and foreign trade controls (export controls and sanctions laws of the UN, the EU and US or other relevant regulator) and shall promptly notify the Employer in case it becomes aware or receives notice of a (alleged) violation of any applicable law. For the purposes of clarity: - The Contractor will not give, promise or attempt to give or approve the giving of anything of value to any person, for illegal purposes or for improperly obtaining or retaining business. |

|  | - The Contractor shall not deal, or cause the Employer to deal with, any person or entity in respect of transactions prohibited by foreign trade controls, except with Employer’s prior written consent; or which could damage the Employer’s commercial or other reputation interests, even if not in violation of any foreign trade controls. The Contractor has established processes, shall maintain policies and procedures to prevent violation of this Sub-Clause, and the Contractor shall maintain adequate records to verify and demonstrate its compliance with these provisions. The Contractor shall, upon written request from the Employer, confirm in writing its compliance with any of the provisions in this Sub-Clause 4.27 and provide any demonstration or proof of compliance as requested. If the Contractor breaches any of its obligations or representations in this clause, the Employer may terminate this Agreement with immediate effect without incurring any liability in accordance with Sub-Clause 15.2 (Termination by Employer) The Contractor shall indemnify, defend and hold harmless the Employer from all fines, penalties and all associated expenses arising out of or resulting from a violation of any of its obligations under this Sub-Clause 4.27. |
| --- | --- |
| ##### Sub-Clause 4.28 Compliance Auditing | Add the following new Sub-Clause 4.28 after Sub-Clause 4.27 The Employer shall have the right to appoint an Employer’s Auditor to audit and verify all matters in connection with the Contractor’s compliance with the Contract. The Contractor shall cooperate with the Employer’s Auditor, provide access to all relevant sites and arrange interviews with all relevant personnel of the Contractor or any Subcontractor. If the Employer’s Auditor determines any concerns, the Contractor shall without any undue delay present the Employer with an improvement plan, which shall ensure that all such concerns are dealt with and remediated in a manner satisfactory to the Employer. |
| Clause – 5 : Design |  |
| ##### Sub-Clause 5.4 Technical Standard & Regulations | INSERT between the first and second paragraph: The Contractor shall pass to the Engineer and Employer approvals received by the Contractor in connection with the Country's technical standards or Laws applicable to the Works. When requested to do so by the Engineer, the Contractor shall provide evidence that he has complied with all such technical standards and Laws. |

| Clause – 6 : Staff and Labour |  |
| --- | --- |
| ##### Sub-Clause 6.5 Working Hours | Delete the whole Sub-Clause and substitute: Working hours are unrestricted and assumed to be 24 hours per day 7 days per week unless otherwise governed by Laws and Regulations in India. |
| ##### Sub-Clause 6.7 ##### Health and Safety | Add the following sentence at the end of the second paragraph: The Contractor shall comply with all statutory requirements, the Employer’s safety policy and any reasonable direction issued by the Employer’s safety department or authorised personnel of the Employer as may be issued from time to time. The cost of the provision of all safety precautions, equipment and clothing shall be borne by the Contractor. All works shall be carried out in a safe manner and free from any danger and shall comply with the relevant Laws regarding safety of the Works. |
|  | All personnel who are in the work area and / or within the operations area of the Employer shall continually wear protection helmets and appropriate boots, and safety vests and belts when they are required by the Laws. Workers shall either wear high visibility vests or jackets or shall have appropriate high visibility adhesive stripes attached to their clothing. Life Jackets shall be worn by all staff working near and over water. The Contractor shall take all precautions necessary to protect the health and safety of persons where works may expose workmen and other persons on, or within the vicinity of the site, to conditions which are dangerous or potentially dangerous to health, including the noxious effects of dust, fumes, liquids, infection, fire, explosion, radiation, or other hazards. |
| ##### Sub-Clause 6.8 Contractors Superintendence | At the end of Sub-Clause 6.8 INSERT: A reasonable proportion of the Contractor's superintending staff shall be able to understand and communicate in English, Hindi or Gujarati. |
| Sub-Clause 6.9 ##### Contractor’s Personnel | Add sub-paragraph (e) to the end of the first paragraph (d) (e) be determined to have engaged in corrupt, fraudulent or coercive practice during the execution of the Works Add the following paragraphs at the end of Sub-Clause 6.9: “If the key personnel named in the Contractor’s proposal could not be in place on the date as per the intent of the Sub-Clause 8.3 [Programme]; the Engineer may suspend that part of the Works until those key personnel, or a suitably replacement staff is provided. The replaced key personnel shall be equal to or better than the original proposed key personnel in terms of experience and qualification. Consent of such replaced personnel shall be obtained from the Engineer by the Contractor, before putting such replaced personnel in place. Any cost and time effect of such suspension of part of the Works shall be borne by the Contractor.” |
| Sub-Clause 6.10 Records of Contractors Personnel and Equipment | Delete Sub-Clause 6.10 and substitute the following; The Contractor shall submit, to the Engineer, details showing the number of each class of Contractor’s Personnel and of each type of Contractors Equipment on the Site. The records shall include the names, ages, genders, hours worked and wages paid to all workers. Details shall be submitted each calendar month, in a form approved by the Engineer, until the Contractor has completed all work which is known to be outstanding at the completion date stated in the Taking-Over Certificate for the Works. |
| ##### New Sub-Clause 6.12 ##### Employment of Local Personnel | Add the following new Sub-Clause 6.12 after Sub-Clause 6.11: The Contractor is encouraged, to the extent practicable and reasonable, to employ staff and labour from sources within India. |
| ##### New Sub-Clause 6.13 ##### Foreign Staff and Labour | Add the following new Sub-Clause 6.13 after new Sub-Clause 6.12: The Contractor may import any personnel who are necessary for the execution of the Works. The Contractor must ensure that these personnel are provided with the required residence visas and work permits. The Contractor shall be responsible for the repatriation Contractor's non- local Personnel. In the event of the death in the Country of any of these personnel or members of their families, the Contractor shall similarly be responsible for making the appropriate arrangements for their return or burial. |

| ##### New Sub-Clause 6.14 ##### Measures against Insect and Pest Nuisance | Add the following new Sub-Clause 6.14 after new Sub-Clause 6.13: The Contractor shall at all times take the necessary precautions to protect all staff and labour employed on the Site from insect and pest nuisance, and to reduce their danger to health. The Contractor shall provide suitable prophylactics for the Contractor's Personnel and shall comply with all the regulations of the local health authorities, including use of appropriate insecticide. |
| --- | --- |
| ##### New Sub-Clause 6.15 ##### Alcoholic Liquor and Drugs | Add the following new Sub-Clause 6.15 after new Sub-Clause 6.14: The Contractor shall not, in accordance with the Laws of the Country, import, sell, give, barter or otherwise dispose of any alcoholic liquor or drugs, or permit or allow importation, sale, gift, barter or disposal by Contractor's Personnel. |
| ##### New Sub-Clause 6.16 ##### Arms and Ammunition | Add the following new Sub-Clause 6.16 after new Sub-Clause 6.15: The Contractor shall not give, barter or otherwise dispose of to any person, any arms or ammunition of any kind, or allow Contractor's Personnel to do so. |
| ##### New Sub-Clause 6.17 ##### Festivals and Religious Customs | Add the following new Sub-Clause 6.17 after new Sub-Clause 6.16: The Contractor shall respect the Country's recognised festivals, days of rest and religious or other customs. |
| ##### New Sub-Clause 6.18 ##### Supply of Food stuffs | Add the following new Sub-Clause 6.18 after new Sub-Clause 6.17: The Contractor shall arrange for the provision of a sufficient supply of suitable food as may be stated in the Specification at reasonable prices for the Contractor's Personnel for the purposes of or in connection with the Contract. |
| ##### Sub-Clause 6.19 ##### Funeral Arrangements | Add the following new Sub-Clause 6.19 after new Sub-Clause 6.18: The Contractor shall be responsible, to the extent required by local regulations, for making any funeral arrangements for any of his local employees who may die while engaged under the Works. |
| ##### Sub-Clause 6.20 ##### Forced or Compulsory Labour | Add the following new Sub-Clause 6.20 after new Sub-Clause 6.19: The Contractor shall not employ "forced or compulsory labour" in any form. "Forced or compulsory labour" consists of all work or service, not voluntarily performed, that is extracted from an individual under threat of force or penalty. |
| ##### Sub-Clause 6.21 Prohibition of Harmful Child Labour | Add the following new Sub-Clause 6.21 after new Sub-Clause 6.20: The Contractor shall not employ any child to perform any work that is economically exploitative, or is likely to be hazardous to, or to interfere with, the child's education, or to be harmful to the child's health or physical, mental, spiritual, moral, or social development. |
| ##### Sub-Clause 6.22 Employment Records of Workers | Add the following new Sub-Clause 6.22 after new Sub-Clause 6.21: The Contractor shall keep complete and accurate records of the employment of labour at the Site. The records shall include the names, ages, genders, hours worked, and wages paid to all workers. These records shall be summarised on a monthly basis and shall be available for inspection by the Engineer, during normal working hours. These records shall be included in the details to be submitted by the Contractor under Sub-Clause 6.10 Records of Contractor's Personnel and Equipment. The Contractor is encouraged, to the extent practicable and reasonable, to employ staff and labour with appropriate qualifications and expertise from sources within the Country. |
| Clause – 7 : Plant, Material and Workmanship |  |
| ##### Sub-Clause 7.4 Testing | Add the following paragraph at the end of the Sub-Clause: “The Contractor shall not be released from any liability or obligation under the Contract by reason of any such inspection or testing or witnessing of testing, or by the submission of reports of inspection or testing to the Engineer.” |

| ##### Sub-Clause 7.6 Remedial Work | Add the following paragraph at the end of the Sub-Clause: In addition to the costs for the removal of improper work, materials or plant, the Contractor shall be liable for the additional costs of the Engineer's services in supervising and administering these works. These costs shall be determined as the additional amount charged by the Engineer to the Employer for the provision of engineering services related to this item. |
| --- | --- |
| Clause – 8 : Commencement, Delays and Suspension |  |
| ##### Sub-Clause 8.1 Commencement of Work | In the second sentence delete “42 days” and insert “14 days” from the date of LOA”. |
| ##### Sub-Clause 8.3 Programme | Delete the first paragraph and substitute: The Contractor shall submit a detailed time programme to the Engineer within 7 days after receiving the notice under Sub-Clause 8.1 (Commencement of Works). The Contractor shall also submit a revised programme whenever the previous programme is inconsistent with actual progress or with the Contractor's obligations including whenever the Engineer has granted an extension of time to complete the Works under Sub-Clause 3.5 and 20.1. Add the following paragraphs at the end of the Sub-Clause: For the avoidance of doubt, the Contractor will only be entitled to an extension of Time for Completion provided it has made all reasonable proper efforts to mitigate any delay. Any failure by the Employer to rely upon any antecedent breach of a condition precedent will not amount to a waiver by the Employer of its rights in this respect. Further, where more than one event causes concurrent delays and the cause of at least one of those events, but not all of them, is a cause of delay which would not entitle the Contractor to an extension of time then to the extent that the delays are concurrent, the Contractor will not be entitled to an extension of time. |

| ##### Sub-Clause 8.4 Extension of Time for Completion | elete sub-paragraphs (a) to (e) and substitute: - a Variation (unless an adjustment to the Time for Completion has been agreed under Sub-Clause 13.3 [Variation Procedure] - a cause of delay giving an entitlement to extension of time under the following provisions of this Contract: - Sub-Clause 1.9 [Delayed Drawings or Instructions]; - Sub-Clause 2.1 [Right of Access to the Site]; - Sub-Clause 4.12 [Unforeseeable Physical Conditions] - Sub-Clause 4.24 [Fossils]; - Sub-Clause. 7.4 [Testing]; - Sub-Clause 8.5 [Delays Caused by Authorities]; - Sub-Clause 10.3 [Interference with Tests on Completion]; - Clause 13 [Variations and Adjustments]; - Sub-Clause 16.1 [Contractor’s Entitlement to Suspend Work]; - Sub-Clause 17.4 [Consequences of Employer's Risks]; and - Sub-Clause 19.4 [Consequences of Force Majeure]; - any suspension of the Works pursuant to Sub-Clause 8.8 [Suspension of Work] (except if and to the extent that such suspension arises by reason of the Contractor’s default); or - any default, negligence or act of prevention on the part of the Employer, his employees, Third Party Contractors or the Engineer in connection with the Works. Add the following paragraphs at the end of the Sub-Clause: For the avoidance of doubt, the Contractor will only be entitled to an extension of Time for Completion provided it has made all reasonable proper efforts to mitigate any delay. Any failure by the Employer to rely upon any antecedent breach of a condition precedent will not amount to a waiver by the Employer of its rights in this respect. Further, where more than one event causes concurrent delays and the cause of at least one of those events, but not all of them, is a cause of delay which would not entitle the Contractor to an extension of time then to the extent that the delays are concurrent, the Contractor will not be entitled to an extension of time. |
| --- | --- |
| ##### Sub-Clause 8.5 Delay Caused by Authority | At the end of Sub-Clause 8.5 INSERT: Further, where more than one event causes concurrent delays and the cause of at least one of those events, but not all of them, is a cause of delay which would not entitle the Contractor to an extension of time then to the extent that the delays are concurrent, the Contractor will not be entitled to an extension of time. |
| ##### Sub-Clause 8.7 ##### Delay Damages | Add the following paragraphs at the end of the Sub-Clause: The Contractor agrees that the amount of liquidated damages payable in accordance with Sub-Clause 8.7 [Delay Damages] for delay in achieving the relevant Time for Completion constitute a genuine pre-estimate of the loss that would be suffered by the Employer as a result of the Contractor's non-compliance with his obligations under Sub-Clause 8.2 [Time for Completion]. If and to the extent that the obligation to pay such delay damages is unenforceable for any reason, the Contractor shall be liable to pay general damages in respect thereof. If the Engineer extends the Time for Completion under Sub-Clause 8.4 after delay damages have been paid or otherwise accounted for under this Sub-Clause, the extension of the Time for Completion shall not invalidate the Employer's claim for delay damages. In such circumstances the Contractor's liability to pay delay damages shall be limited to the sum due on the basis of the new Time for Completion, and the Employer shall repay or otherwise account for the difference between that sum and the sum which has been paid or otherwise accounted for on the basis of the Employer's claim before the extension of the Time for Completion. Interest shall not be payable by the Employer on any amounts payable or repayable under this Sub-Clause. Once the applicable limit of delay damages is reached, the Employer will be able to suspend this contract and hire third parties to complete the Works. Any cost associated with the hiring of third parties to complete the Works shall be recovered from the Contractor. |
| ##### Sub-Clause 8.8 Suspension of Work | At the end of Sub-Clause 8.8 INSERT: Without prior written approval from Engineer to do otherwise, throughout any suspension, the Contractor will maintain its staff and labour resources ready to recommence work, unless agreed otherwise with the Engineer. The Contractor will notify the Engineer of details of any of its staff and labour that it proposes to redeploy to other projects and the Engineer may instruct the Contractor not to so redeploy any staff or labour it considers to be key to the project. |
| ##### Sub-Clause 8.9 Consequences of Suspension | At the end of Sub-Clause 8.9. INSERT: If the Engineer suspends progress of part or all of the Works in order to mitigate or prevent a risk to the environment or to the health or safety of Contractor’s Personnel, visitors, and adjacent communities to the Site, the Contractor shall not be entitled either to an extension of time for, or to payment of the Cost incurred in relation to that. |
| ##### Sub-Clause 8.11 Prolonged Suspension | Substitute the wording of the last sentence with: “If the suspension affects the whole of the Works and the suspension has continued for an uninterrupted period of 90 days the Contractor may give notice of termination under Sub-Clause 16.2 [Termination by Contractor]”. |
| ##### New Sub-Clause 8.13 ##### Other Contractors | Add the following to Sub-Clause 8.13 after sub clause 8.12 The Contractor shall take due account of the presence of other contractors, employed by the Employer or by other parties, who may be working immediately adjacent to or overlapping with the Contractor’s Site during part or all of the Contract period in accordance with the provisions of Sub-Clause 4.6. The Contractor will be deemed to have taken all reasonable steps to avoid delay and interference with or from these other contractors and will not be entitled to any extension of Time for Completion as a result of such other contractors. |
| Clause – 9 : Tests on Completion |  |
| ##### Sub-Clause 9.1 Contractor’s Obligations | Delete the first paragraph and substitute: The Contractor shall carry out the Tests on Completion required by the Specification in accordance with this Clause and Sub-Clause 7.4 [Testing], after providing the documents in accordance with Sub-paragraph (d) of Sub- Clause 4.1 [Contractor's General Obligations]. |
| Clause – 11 : Defect Liability |  |
| ##### Sub-Clause 11.1 ##### Completion of Outstanding Work and Remedying Defects | Add the words “defined in Appendix to the Tender” after “Defects Notification Period” in the first paragraph. |
| Clause – 12 : Tests after Completion |  |
| ##### Sub-Clause 12.4 Failure to pass tests after completion | DELETE the first paragraph. This Sub-Clause shall now commence “If the Works, or a Section……” |
| Clause – 13 : Variation & Adjustment |  |
| Sub-Clause 13.1 Right to Vary | Add the following paragraph at the end of the Sub-Clause. The Employer reserves the right to reduce or delete certain aspects of the Works including items of the Works specified as “Optional” during the construction period by informing the Engineer and Contractor in writing of proposed changes. Calculation of the amended value of work reduced or deleted shall be based on measured work at the rates defined in the Schedules. Add the following before the last paragraph of Sub-Clause 13.1: The Employer may omit and/or reduce any work of the Contract and the Contractor is not deemed to be entitled for any compensation or revision of Contract rates in regard with such omission and/or reduction, provided: - the total value of such omissions and/or reductions does not exceed 25% of the accepted Contract Price; and - the Employer notifies in writing the omission and/or reduction of the work prior to the Contractor commencing the procurement or other actions of the execution of such work. |
| Clause – 14 : Contract Price and Payment |  |
| ##### Sub-Clause 14.1 Contract Price | Delete sub-paragraph (b) and substitute; - The Contract Price includes all duties, taxes (except GST), materials royalties including No Due Certificate from Mining Department of GOG, TCS, Labour Cess, BOCW Cess, premiums for various insurances, licenses and fees that may be levied in accordance with the Laws and regulations in force as on the Base Date on the Contractor's Equipment, Plant, Materials and supplies acquired for the purpose of the Contract and on the services performed under the Contract. The GST shall be paid extra as per the prevailing rates. The Contract Price shall include expenditure for traffic maintenance to avoid constraints of work, safety, diversion and any precautions required to execute the works and expenditure for liaising/dispute resolve with local authorities/villages which is also in the scope of the Contractor. Add the following after the last paragraph: Nothing in the Contract shall relieve the Contractor from its responsibility to pay any tax including any tax that may be levied in India on profits made by it in respect of the Contract. |
| ##### Sub-Clause 14.2 Advance Payment | Delete the last sentence of the third paragraph and substitute: This guarantee shall be in the form annexed as Annex III issued by a Scheduled Bank (as defined in the “Reserve Bank of India Act, 1934”) to be proposed by the Contractor and approved in advance in writing by the Employer. Delete the sub-paragraph (a) of 5th paragraph of Sub-Clause 14.2 and substitute with the following: - “The Employer shall start recovery of Advance payment from the payment certificate in which the total of all certified payments (excluding the advance payment and deductions and repayments of retention) exceeds 10% (ten percent) of the Contract Price less Provisional Sums, until such time as the advance payment has been repaid; always provided that the advance payment shall be completely repaid prior to the time when 80% of the Contract Price has been certified for payment; and” Delete the words “one quarter (25%)” and substitute with “twenty percent (20%)” in the first line of sub-paragraph (b) of 5th paragraph. |
| ##### Sub-Clause 14.7 ##### Payment | Delete last para and replace with new paragraph as follows: ''Payments will be made to the Contractor to their Bank a/c through electronic payment mode through National Electronic Fund Transfer (NEFT) or as amended from time to time”. |
| ##### Sub-Clause 14.8 ##### Delayed Payment | Delete Sub-Clause 14.8 in its entirety |
| ##### Sub-Clause 14.16 Dues and Duties | Add the following new Sub-Clause 14.16 after new Sub-Clause 14.15: The Contractor shall pay, such rates and prices defined by him in the Contract Price which shall include but not limited, all freight and insurance charges, harbour dues, pilotage, wharfage, port rates, tolls landing charges, octroi and all other dues in respect of plant and equipment, ancillaries, spares, lubricants, etc imported into India and brought into Gujarat in connection with the Works. This is excluding any port charges which will otherwise be levied by the Gujarat Pipavav Port Limited. |
| ##### Sub-Clause 14.17 Local Taxation | Add the new Sub-Clause 14.17 after Sub-Clause 14.16: The Contract Price shall be exclusive of Gujarat/Central Goods Service Tax, but include all customs duties, import duties, business taxes, and income and other taxes duties, cess, Labour cess, levies, royalties, etc. that may be levied in accordance with the laws and regulations in being on the date 28 days prior to the latest date for submission of bids in the Employer's country on the Contractor's Equipment, and supplies (temporary and consumable) acquired for the purpose of the Contract and on the services performed under the Contract. Nothing in the Contract shall relieve the Contractor from his responsibility to pay any tax that may be levied in the Employer's country on profits made by him in respect of the Contract. |
| ##### Sub-Clause 14.18 Personal Income Taxes | Add the new Sub-Clause 14.18 after Sub-Clause 14.17: The Contractor's Personnel will be liable to pay personal income taxes in the Employer's country in respect of such of their salaries and wages as are chargeable under the laws and regulations for the time being in force, and the Contractor shall perform such duties in regard to such deductions thereof as may be imposed on him by such Laws and regulations. |
| Clause – 15 : Termination by Employer |  |
| ##### Sub-Clause 15.2 Termination by Employer | Add new sub-paragraphs (g), (h) and (i) as follows: (g) fails to comply with Sub-Clause 4.8 [Safety Procedures], (h) fails to comply with a notice served by the Employer pursuant to Sub-Clause 4.26 [Breach of Supplier Code of Conduct], or (i) fails to comply with Sub-Clause 4.27 [Anti-Corruption and Export Control Compliance], DELETE in the third paragraph “in the case of sub-paragraph (e) or (f)” and REPLACE by “in the case of sub-paragraph (e), (f), (g), (h) or (i)”. |

| ##### Sub-Clause 15.5 Employer’s Entitlement to Termination | Add the following paragraphs at the end of the Sub-Clause: If the Employer determines that the Contractor has engaged in corrupt, fraudulent, collusive or coercive practices, in competing for or in executing the Contract, then the Employer may, after giving 14 days' notice to the Contractor, terminate the Contractor's employment under the Contract and expel him from the Site, and the provisions of Clause 15 shall apply as if such expulsion had been made under Sub-Clause 15.2 (Termination by Employer). Should any employee of the Contractor be determined to have engaged in corrupt, fraudulent or coercive practice during the execution of the Works then that employee should be removed in accordance with Sub-Clause 6.9 [Contractor's Personnel]. |
| --- | --- |
| Clause – 16 : Suspension and Termination by Contractor |  |
| ##### Sub-Clause 16.1 Contractors Entitlement to Suspend Work | DELETE in the first paragraph “or the Employer fails to comply with Sub-Clause 2.4 [Employer's Financial Arrangements]” Delete the words “to the Engineer” in line 3 of the fourth paragraph and replace by “to the Employer and to the Engineer”. |
| ##### Sub-Clause 16.2 Termination by Contractor | DELETE sub-paragraph (a). |
| ##### Sub-Clause 16.4 Payment on Termination | In sub-paragraph (c) DELETE “loss of profit or other loss or”. |
| Clause – 17 : Risk & Responsibility |  |
| ##### Sub-Clause 17.1 Indemnities | INSERT sub-paragraph (c) as follows: - and, any breach by the Contractor of its obligations under Sub-Clauses 4.25 [Third Party Code of Conduct], 4.26 [Breach of Third-Party Code of Conduct] or 4.27 [Export Control]. |
| ##### Sub-Clause 17.3 Employers Risks | At the end of the first sentence INSERT “insofar as they directly affect the execution of the Works in the Country”. |
| ##### Sub-Clause 17.4 Consequences of Employer’s Risks | Delete the words “to the Engineer” in line 3 of the first paragraph and line 2 of the second paragraph and replace by “to the Employer and to the Engineer”. |

| ##### Sub-Clause 17.6 Limitation of Liability |  | In the first line of the second paragraph, insert “cumulative” after the word “total”. At the end of the second paragraph, replace the words “the sum stated in the Particular Conditions or (if a sum is not so stated) the Accepted Contract Amount” with the words “ten percent (10%) of the Contract Price, including without limitation Delay Damages. The foregoing is without prejudice to the right of Contractor to avail itself of the benefits of the Convention on Limitation of Liability for Maritime Claims”. At the end of Sub-Clause 17.6 INSERT: This Sub-Clause shall not apply to a breach by the Contractor of any of Sub-Clauses 1.13 [Compliance with Laws], 4.25 [Third Party Code of Conduct], 4.26 [Breach of Third-Party Code of Conduct] or 4.27 [Export Control]. |
| --- | --- | --- |
| Clause – 18 : Insurance |  |  |
| ##### Sub-Clause 18.2 Insurance for Works and Contractors Equipments | DELETE the entire Sub-Clause and SUBSTITUTE: The insuring Party shall insure the Works, Plant, Materials and Contractor’s Documents for not less than the full Accepted Contract Amount and including a provision for the costs of demolition, removal of debris, professional fees and profit. This insurance shall be effective from the Commencement Date until the date of issue of the Taking-Over Certificate for the Works. The insuring Party shall maintain this insurance to provide cover until the date of issue of the Performance Certificate, for loss or damage for which the Contractor is liable arising from a cause occurring on the Site, including storage, disposal, borrow pit and any other working areas, after the Commencement Date and prior to the issue of the Taking-Over Certificate, and for loss or damage caused by the Contractor on the Site, including storage, disposal, borrow pit and any other working areas, in the course of any other operations (including those under Clause 11 [Defects Liability] and Clause 12 [Tests after Completion]). The insuring Party shall insure the Contractor's Equipment for not less than the full replacement value, including delivery to Site. For each item of Contractor's Equipment, the insurance shall be effective while it is being transported to the Site and until it is no longer required as Contractor's Equipment. |  |

|  | If the Contractor’s Equipment includes vessels, items of floating equipment or watercraft, the insuring Party shall effect, or require that the owners effect, and maintain charterer’s liability insurance, customary material damage, hull and machinery insurance with limits of liability of the full replacement cost of the vessel, items of floating equipment or watercraft, and protection and indemnity insurance for a limit of not less than USD 5,000,000 for any one occurrence or series of occurrences arising out of one event Unless otherwise stated in the Particular Conditions, insurances under this Sub-Clause: - in relation to the Works, Plant, Materials and Contractor’s Documents located on the Site, including storage, disposal, borrow pit and any other working areas, shall be effected and maintained by the Employer as insuring Party; - in relation to the Plant, Materials and Contractor’s Documents located off the Site, including in the course of transit to and from the Site within the Country, shall be effected and maintained by the Employer as insuring Party. For transit to and from locations outside the Country, the Contractor shall be the insuring Party, naming the Employer and Lenders as co-insured. In the event of transits of any Plants and Materials critical to the timely completion of the Project, the Employer reserves the right to be the insuring Party; - in relation to the Contractor's Equipment, shall be effected and maintained by the Contractor as insuring Party; and - coverage for the Works, Plant, Materials and Contractor’s Documents shall be in the joint names of the Parties, who shall be jointly entitled to receive payments from the insurers, payments being held or allocated between the Parties for the sole purpose of rectifying the loss or damage. The Contractor shall bear the cost of any deductibles applying to any insurance claims made on the Employer’s insurance policies which arise from occurrences or events for which the Contractor is responsible under the contract or otherwise and shall, in making any claim, comply with the Employer’s insurance claims procedure. The Contractor shall make all of his Subcontractors and suppliers aware of this obligation. All insurances to be effected by the Employer under this contract shall be with insurers and on terms to be approved solely by the Employer. The Contractor shall be deemed to have satisfied himself and shall cause all of his Subcontractors and suppliers to satisfy themselves with regard to the extent of cover provided under the policies of insurance effected by the Employer. The Contractor is deemed to have read and understood all the terms of the insurance provided by the Employer. If, in the Contractor’s opinion, the amounts and/or risks insured are insufficient to cover the Contractor’s duties, obligations and liabilities under this contract or otherwise, the Contractor may effect such further insurance at Contractor’s own cost. The Contractor shall for himself and on behalf of all his Subcontractors and suppliers accept the insurance policies effected by the Employer as if they had been arranged by him directly and shall with all due diligence observe and fulfil and procure that his Subcontractors and suppliers observe and fulfil the terms contained in the said policies. - Parties hereby agree that in any type of insurance as herein provided, the insurance institution shall waive its right to subrogate against the Employer in connection with the insurance. |
| --- | --- |
| ##### Sub-Clause 18.3 Insurance against Injury to Persons and Damage to Property | DELETE the entire sub-paragraphs (c) and (d) up to the end of the Sub-Clause. |
| Sub-Clause 18.4 Insurance for Contractors Personnel | Delete the words “The Contractor” in line 1 of the first paragraph and replace by “Pursuant to Workers Compensation legislation or any other law amending or replacing such legislation, the Contractor”. Delete the second paragraph and substitute: The insurance shall cover the Employer and the Engineer against liability for claims, damages, losses and expenses (including legal fees and expenses) arising from injury, sickness, disease or death of any person employed by the Contractor or any other of the Contractor's Personnel, except this insurance may exclude losses and claims to the extent that they arise from any act or neglect of the Employer or the Employer's Personnel. Add the following paragraph at the end of the Sub-Clause: Provided the Contractor will not be required to take out any Workmen's Compensation Insurance Policy if the workers employed in the Works are eligible for coverage under any employee’s social security laws and regulations that may be in place and are so covered. The Contractor shall register his employees and contribute under the relevant social security scheme in the places where the scheme is implemented and comply with the provisions of the relevant laws and regulations. He shall submit the code Number and Insurance Numbers of all the workers on site to the Engineer for checking. |
| ##### New Sub-Clause 18.5 Insurance for Design | Add the new Sub-Clause 18.5 after Sub-Clause 18.4: The Contractor shall effect professional indemnity insurance, which shall cover the risk of the Contractor being in breach of its design obligations in respect of the Works. This Insurance shall be for a limit of not less than USD 1,000,000 per occurrence. The Contractor shall maintain the professional indemnity insurance in full force and effect until five years after issue of the Taking-Over Certificate. The Contractor shall notify the Employer promptly of changes to this insurance. |
| ##### New Sub-Clause 18.6 Additional Insurances | Add the new Sub-Clause 18.6 after new Sub-Clause 18.5: The Contractor shall effect and maintain, in full force until the works are delivered to Employer, subject to the terms set forth herein, the following insurances with a triple “A” insurance company, incorporated in the Country, satisfactory to Employer, duly authorized to do business in the Country: - Automobile liability Insurance against claims by third parties in respect of bodily injury (including death) and property damage arising out of and in connection with the use of all owned, leased, non-owned and hired vehicles used in connection with the performance of the Works in accordance with statutory obligations and for the following minimum limits: |
|  | - in respect of bodily injury (including death), on an unlimited basis; and - in respect of property damage, on a USD 1,000,000 any one occurrence unlimited as to the number of claims basis. - Civil liability caused by cargo in transit including hazardous cargo As regards to cargo vehicles that transport raw materials, equipment and/or materials used in the construction of the Works, same shall have the coverage of civil liability for damages related to the cargo, and if required by the scope of the construction works as provided in these Conditions, it shall have coverage of civil liability for any for hazardous cargo. This insurance shall be in an amount not less than the responsibility limits of USD 1,000,000 per occurrence or arising from same event and shall include a contractual liability insurance applicable to Contractor’s obligations. |
| ##### New Sub-Clause 18.7 ##### Professional Indemnity Insurance | Add the following new Sub-Clause 18.7 after new Sub-Close 18.6: The Employer shall procure and implement its own OCIP (Owners Control Insurance Policy) CAR (Construction All Risks). The detail of the insurance terms is included in this document. |
| ##### Sub-Clause 18.8 ##### War Risk Insurance | Add the following new Sub-Clause 18.8 after new Sub-Close 18.7: If the Contractor receives instructions from the Employer to insure against War Risk, such insurance if available shall be effected, at the cost of the Employer, with an Insurance Company acceptable to the Employer and shall be in the joint names of the Contractor and the Employer. |
| ##### Sub-Clause 18.9 ##### Additional Insurance | Add the new Sub-Clause 18.9 after new sub clause 18.8 The Contractor shall effect and maintain, in full force until the works are delivered to Employer, subject to the terms set forth herein, the following insurances with an “A” insurance company, incorporated in the Country, satisfactory to Employer, duly authorized to do business in the Country: - Automobile liability - Insurance against claims by third parties in respect of bodily injury (including death) and property damage arising out of and in connection with the use of all owned, leased, non-owned and hired vehicles used in connection with the performance of the Works in accordance with statutory obligations and for the following minimum limits: - in respect of bodily injury (including death), on an unlimited basis; and - in respect of property damage, on a USD 1,00,000 any one occurrence unlimited as to the number of claims basis. Civil liability caused by cargo in transit including hazardous cargo As regards to cargo vehicles that transport raw materials, equipment and/or materials used in the construction of the Works, same shall have the coverage of civil liability for damages related to the cargo, and if required by the scope of the construction works as provided in these Conditions, it shall have coverage of civil liability for any for hazardous cargo. This insurance shall be in an amount not less than the responsibility limits of USD 1,00,000 per occurrence or arising from same event and shall include a contractual liability insurance applicable to Contractor’s obligations. |
| Clause – 19 : Force Majeure |  |
| Sub-Clause 19.1 Definition of Force Majeure | Delete Sub-Clause 19.1 and substitute the following: In this Clause, “Force Majeure” means an exceptional event or circumstance: - which is beyond a Party’s control, - which such Party could not reasonably have provided against before entering into the Contract, - which, having arisen, such Party could not reasonably have avoided or overcome, - which is not substantially attributable to the other Party, and - which prevents a Party from performing all or a substantial part of its obligations pursuant to the Contract. Force Majeure may include, but is not limited to, exceptional events or circumstances of the kind listed below, so long as conditions (a) to (d) above are satisfied: - war, hostilities (whether war be declared or not), invasion, act of foreign enemies, - rebellion, terrorism, revolution, insurrection, military or usurped power, or civil war, - (riot, commotion, disorder, strike or lockout by persons other than the Contractor’s Personnel and other employees of the Contractor and Sub- contractors, - munitions of war, explosive materials, ionising radiation or contamination by radio-activity, except as may be attributable to the Contractor’s use of such munitions, explosives, radiation or radio-activity or to the Contractor’s failure to ensure the removal of UXO in accordance with Sub-Clause 4.25 [Removal of Utilities and Man-Made Obstacles and Unexploded Ordnance];, and - natural catastrophes arising from the forces of nature such as earthquake or volcanic activity but excluding climatic activity. For the sake of clarity Force Majeure excludes; - any operation of the forces of nature unless these give rise to a natural catastrophe any natural physical conditions and man- made and other physical obstructions and pollutants, which the Contractor encounters at the Site |
| Clause – 20 : Claims, Disputes and Arbitration |  |
| ##### Sub-Clause 20.1 Contractors Claims | After sub-paragraph (c) INSERT: If the Contractor fails to submit claim within the 42 day period described above, a detailed claim including supporting particulars of the basis of the claim and of the extension of time and/or additional payment claimed, then the Time for Completion shall not be extended, the Contractor shall not be entitled to additional payment and the Employer shall be discharged from all liability in connection with the claim. Before the final paragraph INSERT: If the Engineer does not respond within such period, the Employer shall instruct the Engineer to do so, upon failure of which within the timeframe set by the Employer after consultation with the Contractor, the claim shall be deemed rejected by the Engineer and either Party may refer to the Dispute Adjudication Board in accordance with Sub-Clause 20.4 [Obtaining Dispute Adjudication Board's Decision]. |
| ##### Sub-Clause 20.2 Appointment of the Dispute Adjudication Board | In the first paragraph, DELETE the last sentence and SUBSTITUTE: “The Parties shall jointly appoint a DAB by the date stated in the Appendix to Tender.” In the sixth paragraph, after “the three members” and “shall be” INSERT: “, including remuneration of any expert whom the DAB consults,” After the sixth paragraph INSERT: If at any time the Parties so agree, they may jointly refer a matter to the DAB for it to give its opinion. Neither Party shall consult the DAB on any matter without the agreement of the other Party. DELETE the last paragraph and SUBSTITUTE: Unless otherwise agreed by both Parties, the appointment of the DAB (including each member) shall expire when the discharge referred to in Sub-Clause 14.12 [Discharge] shall have become effective. |
| ##### Sub-Clause 20.6 Arbitration | Add new sub-paragraph (d) after sub-paragraph (c) - The arbitration shall take place in Ahmedabad, Gujarat Add the following paragraph at the end of the Sub-Clause: The law governing this Clause 20 will be the governing law of the contract as stated in the Appendix to Tender. Where disputes arise under this Contract and under any contract with any contractor identified in Sub-Clause 4.6 (b) or (c) and in the reasonable opinion of the first tribunal to be appointed in any of the disputes those disputes are so closely connected that it is expedient for them to be resolved in the same proceedings, that tribunal shall have the power to order that the proceedings to resolve that dispute shall be consolidated with those to resolve any of the other disputes (whether or not proceedings to resolve those other disputes have yet been instituted), provided that no date for the final hearing of the first arbitration has been fixed. If the tribunal so orders, the parties to each dispute which is a subject of its order shall be treated as having consented to that dispute being finally decided: - by the tribunal that ordered the consolidation unless the International Chamber of Commerce decides that it would not be suitable or impartial; and - in accordance with the procedure, at the seat and in the language specified in the arbitration agreement in the contract under which the tribunal that ordered the consolidation was appointed, save as otherwise agreed by all parties to the consolidated proceedings or, in the absence of such agreement, ordered by the tribunal in the consolidated proceedings. Any award given in relation to this Sub-Clause 20.6 shall include as a minimum a copy of the arbitration agreement, a summary of the Parties’ submissions and documents, the grounds on which the award is made, and the relief granted, the date and place of the award and it shall be signed by the arbitrators. The proceedings shall be conducted, and the award rendered, in the ruling language stated in the Appendix to Tender. |
| ##### Sub-Clause 20.7 Failure to Comply with Dispute Adjudication Board’s Decision | Add the following paragraph at the end of the Sub-Clause: In the event that a Party fails to comply with a decision of the DAB, then the other Party may, without prejudice to any other rights it may have, refer the failure itself to arbitration under Sub-Clause 20.4 [Obtaining Dispute Adjudication Board's Decision] and Sub-Clause 20.5 [Amicable Settlement] shall not apply to this reference. |