Gujarat Pipavav Port Limited

Tender Document

Design, Procure and Construction of Immigration Office at APM Terminals Pipavav

GPPL-BID-001

Volume – 1

Section 4	: Appendix to Tenderer

Appendix to Tender

DESIGN, PROCURE AND CONSTRUCTION OF IMMIGRATION OFFICE AT APM TERMINALS PIPAVAV

NOTE	with the exception of the items for which the Employer’s requirements have been inserted, the following information must be completed before the Tender is submitted)

| Item | Sub-Clause | Data |
| --- | --- | --- |
| Employer's name and address | 1.1.2.2 & 1.3 | Gujarat Pipavav Port Ltd Post Rampara-2 Via Rajula, Distt Amreli Pipavav Port – 365 560 Gujarat (India) T: +91 (0)2794-286001 F: +91 (0)2794-286312 |
| Contractor's name and address | 1.1.2.3 & 1.3 | […………………………………………………………………] |
| Engineer's name and address | 1.1.2.4 & 1.3 | Gujarat Pipavav Port Ltd Post Rampara-2 Via Rajula, Distt Amreli Pipavav Port – 365 560 Gujarat (India) T: +91 (0)2794-286001 F: +91 (0)2794-286312 |
| Time for Completion of the Works | 1.1.3.3 | 180 (One Hundred Eighty) Days from Handing of the Work Site |
| Defects Notification Period | 1.1.3.7 | 365 days from the date of Taking Over Certificate issued by the Employer |
| Electronic transmission systems | 1.3 | Email |
| Governing Law | 1.4 | Laws of India |
| Ruling language | 1.4 | English |
| Language for communications | 1.4 | English |
| Time for access to the Site | 2.1 | [………] days after Commencement Date |
| Amount of Performance Security | 4.2 | 10% of the Accepted Contract Amount. The bank Guarantee shall be issued by a nationalized bank or scheduled commercial bank permitted to carry out business in India by the Reserve Bank of India. |
| Normal working hours | 6.5 | Unrestricted, 24 hours a day, 7 days a week, subject to adherence and compliance of applicable Laws by the contractor |
| Commencement of Works | 8.1 | To be finalized. |
| Delay damages for the Works | 8.7 & 14.15(b) | 0.25% of the final Contract Price per day, |
| Maximum amount of delay damages | 8.7 | 10% of the final Contract Price |
| Total advance payment | 14.2 | 10% of the Accepted Contract Amount only against bank guarantee. The Advance Payment shall be released on submission of unconditional Bank Guarantee for an amount equivalent to one hundred (100) percent of the amount of the advance payment requested by the Contractor. The bank Guarantee shall be issued by a nationalized bank or scheduled commercial bank permitted to carry out business in India by the Reserve Bank of India. |
| Start repayment of advance payment | 14.2 | The repayment of Advance shall be completely repaid prior to the time when 20% to 80% of the Contract Price has been certified for payment. |
| Currencies and proportions | 14.2 | 100% in Indian Rupees |
| Percentage of retention | 14.3 | 10% of each payment |
| Limit of Retention Money | 14.3 | 10% of the final Contract Price |
| Release of Retention Money | 14.3 | After completion of Defect Liability period |
| If Sub-Clause 14.5 applies: |  |  |
| Plant and Materials for payment when shipped en route to the Site | 14.5(b) | ………………[list] ………………[list] |
| Plant and Materials for payment when delivered to the Site | 14.5(c) | ………………[list] ………………[list] |
| Minimum amount of Interim Payment Certificates | 14.6 | 5% of the Accepted Contract Amount |
| Currency of payment | 14.15 | Indian Rupees |
| Periods for submission of insurance: - evidence of insurance - relevant policies | 18.1 18.1 | Prior to mobilization Prior to mobilization |
| Maximum amount of deductibles for insurance of the Contractor’s 's risks | 18.2(d) | Nil |
| Minimum amount of third party insurance | 18.3 | 3% of accepted contract value |
| Professional Indemnity Insurance | 18.6 | 50 million Indian Rupees |
| Date by which the DAB shall be appointed | 20.2 | within 28 days of request by either party |
| The DAB shall be | 20.2 | A DAB of three Members |
| Appointment (if not agreed) to be made by | 20.3 | The President of FIDIC or a person appointed by the President |

Initials of signatory of Tender………………………………………………………………